# CTC-RI PCMH Kids Expansion: July 2019-June 2022 Milestones Summary (updated 6 25 20 with updates noted in blue)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Start Up (MP 1)** **7/1/19-6/30/20** | **Measurement Period 2 (MP 2)** **7/1/20-6/30/21**  | **Measurement Period 3 (MP 3)** **7/1/21-6/30/22** | **Notes** |
| **Meets with Practice Facilitator**  | July 2019-June 20201-2 x per month  | July 2020-June 20211x a month  | July 2021-June 2022Quarterly  | **N/A** |
| **Attends 3 out of 4 Breakfast of Champions; 2 out of 4 PCMH Kids Stakeholder meetings; at least one practice representative at Annual Conference; Practice reporting/transformation are required meetings; NCM/CC are required meetings once NCM/CC hired** | July 2019-June 2020 | July 2020-June 2021 | July 2021-June 2022 | **N/A** |
| **Submit clinical quality data as defined in CTC Performance Standards**  **Clinical quality: MMR for school aged children (4 to 6-year-old) using KIDS NET report comparing 12/31/19 to 12/31/20: target 90% by 12/31/20;** Note: Practices would continue to report BMI with follow up; Developmental Screening, Well Child Adolescent and Lead screening | 1st report due January 15, 2020, April 15,  | **Quarterly****July 15, 2020,** **Oct 15,** **Jan 15, Apr 15** | QuarterlyJuly 15, 2021, Oct 15, Jan 15, Apr 15 | **July 15, 2020: For MMR, Use KIDS NET Report 7/1/19-6/30/20** **Lead screening: waiting for OHIC final guidance** **Submit to:** [**CTC Portal**](https://www.ctc-ri.org/) |
| **Submit reports on high risk patients, as defined by CTC****Add high risk option: School aged children that are behind on immunizations with particular attention to MMR**  | N/A | QuarterlyJuly 15, Oct, Jan and Apr | QuarterlyJuly 15, Oct, Jan and Apr | **Submit to:**[**CTC Portal**](https://www.ctc-ri.org/) |
| **Submits CTC Quarterly Provider Panel Report indicating open/closed panel status and 3rd next available appointment****For MMR: Practice Facilitators will assist practices with identifying “demand” for children school aged that need MMR against “supply; Start planning July**  | QuarterlyAugust, Nov, Feb and May (Due back to CTC 15th)  | QuarterlyAugust, Nov, Feb and May (Due back to CTC 15th)  | QuarterlyAugust, Nov, Feb and May (Due back to CTC15th)  | **Will receive an email from CTC 1st week of month with form that outlines fields to be updated****Submit to:** [**CTC Portal**](https://www.ctc-ri.org/) |
| **Submit to CTC screenshot demonstrating patient access to a secure web portal, for patients to request appointment requests, referrals, and prescription refills and test results**  | N/A | September 31, 2020 | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submits budget and staffing plan and use of funds to support care delivery model to CTC** | September 30, 2019 | N/A | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submits NCQA recognition /renewal work plan to CTC**  | September 30, 2019  |  |  | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submit patient panel for CAHPS survey to approved data vendor** **Use Patient qualitative questionnaire (small sample of 7) to ask parents what would be helpful to them in brining child into practice selecting sample looking at vulnerable populations**  | Fall 2019 | Fall 2020 **Parent questionnaire results by end of July**  | Fall 2021  | **Submit to** **CTC-ri@ctc-ri.org** |
| **Submits to OHIC quality measure information** | October 15, 2019 | October 15, 2020 (includes new measures for baseline)  | October 15, 2021(includes new measures for meeting threshold or improvement)  | **Submit to:**[**OHIC Website**](http://www.ohic.ri.gov/) |
| **Submits to OHIC cost management strategy QI project (per OHIC definition)**  | October 15, 2019 | October 15,2020 | October 15, 2021  | **Submit to:**[**OHIC Website**](http://www.ohic.ri.gov/) |
| **Hire 1.0 Nurse Care Manager (NCM) or Care Coordinator for every 3,000 attributed patients ($2.50 pmpm)** | October 31, 2019 | Maintain staffing  | Maintain staffing  | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Develop high risk registry and process for care plan for patients identified for care management**  | December 31, 2019 | Maintain system  | Maintain system  | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submits Transition of Care Policy and Procedure** | December 31, 2019 | N/A | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submits 1 additional compact with high volume specialist based on needs of patient population as defined by CTC** | N/A | N/A | December 31, 2021 | **Submit to:** **CTC-ri@ctc-ri.org** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Start Up (MP 1)** **7/1/19-6/30/20** | **Measurement Period 2 (MP 2)** **7/1/20-6/30/21**  | **Measurement Period 3 (MP 3)** **7/1/21-6/30/22** | **Notes** |
| **Submits a quality improvement activity demonstrating improvement to improve a performance measure (quality, customer experience, utilization) Recommend MMR PI**  | N/A | January 31, 2021 | January 31, 2022  | **Submit to:** **CTC-ri@ctc-ri.org** |
| **NCM/CC completes standardized learning program as defined by CTC-RI.** | Program Starts January 2020 | N/A | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submit before and after-hours protocol as defined by CTC** | March 31, 2020 | N/A | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Enrolls in Pedi PRN and submits 1 compact for behavioral health** | March 31, 2020 | N/A | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Registers for Q Pass ; for renewal, update 4 months prior to expiration**  | March 31, 2019 | N/A | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submits NCQA PCMH recognition application; for Annual Renewal submit 1 month prior to renewal**  | N/A | March 31, 2021 | N/A | **Submit to:** **CTC-ri@ctc-ri.org** |
| **Submits a quality improvement activity plan for improving clinical quality, customer experience or utilization** **Consider MMR PI plan**  | **May 2020** | May 2021  | May 2022 | **Submit to:** **CTC-ri@ctc-ri.org** |

|  |
| --- |
| **Learning Network Opportunities Attends 3 out of 4 Breakfast of Champions; 2 out of 4 PCMH Kids Stakeholder meetings; at least one practice representative at Annual Conference; Practice reporting/transformation are required meetings; NCM/CC are required meetings once NCM/CC hired; Practices may also be asked to present their work at “best practice sharing” committee meetings**  |
|   | **Year 1** | **Year 2** | **Year 3** |
| **Orientation\***  | April 11, 2019 5:30 to 7:00pm |   |   |
| **Breakfast of Champion (BOC) Events** | May 10, 2019September 13, 2019;December 13,2019 |   |   |
|  March 13, 2020;  | Dates TBD | Dates TBD |
| and June 12, 2020 7:30-9:00am  |   |   |
| **PCMH Kids Stakeholder**  | October 3 2019; | October 1 2020; | October 7, 2021; |
| January 9, 2020 | January 7 , 2021; | January 6., 2022; |
| April 2,2020; | April 1, 2021 | April 7 2022; |
| July 9, 2020 (7:30-8:30am) |  July 8,2021 (7:30-8:30am) |  July 14,2022 (7:30-8:30am) |
| **Practice Reporting/Transformation**  | 4th Wednesday of every month; 7:30 - 8:30 (except months with BOC; no meeting in December)  | 4th Wednesday of every month; 7:30 - 8:30 (except months with BOC; no meeting in December)  | 4th Wednesday of every month; 7:30 - 8:30 (except months with BOC; no meeting in December)  |
| **Nurse Care Manager/Care Coordinator Best Practice Sharing**  | 3rd Tuesday of every month (except month of Annual Conference)  | 3rd Tuesday of every month (except month of Annual Conference)  | 3rd Tuesday of every month (except month of Annual Conference)  |
| **Annual Learning Collaborative** | 24-Oct-19 | Date TBD | Date TBD |